Key improvements sought for QA3

| Standard/element 3.1.1 | Outdoor and indoor spaces, buildings, furniture, equipment, facilities and resources are suitable for their purpose. |  |
| --- | --- | --- |
|  | Identified issue | Bark under the swings keeps being washed away in heavy downpours and the area is not used effectively. (Jan 2012) |

| Standard/element 3.3.2 | Children are supported to become environmentally responsible and show respect for the environment. |  |
| --- | --- | --- |
|  | Identified issue | The vegetable gardens are not maintained on a continual basis. (Jan 2012) |

| Standard/element [number] | [Include the element number (left) and description from QA3 table] |  |
| --- | --- | --- |
|  | Identified issue | [Briefly summarise the issue identified during the self-assessment process, then complete the improvement planning table on the next page. Delete rows not required.] |

| Standard/ element | What outcome or goal do we seek? | Priority (L/M/H) | How will we get this outcome? (Steps) | Success measure | By when? | Progress notes |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1.1 | To design and develop an environmental discovery area in the old swing area. | L | Management to meet and discuss ideas, implications and costs. (Via email and phone Feb & April 2012) Plans for the area revised. Gather information regarding plant types and quotes. Action the changes. | In OH&S checklists, add this area to the maintenance section. Review with parent and child feedback (ask the children what they want.) | To have ideas finalised by end of July and all work completed by end of third term. | Discussions with management regarding ideas for swing area took place: ideas are nature area with sensory walk, plant grasses and use pavers to create windy path. May 2012. |
| 3.3.2 | Children and staff to take part in helping maintain the vegetable gardens at Bumblebee in an ongoing basis. | H | Staff to put in place a roster for each room to participate in the upkeep and management of the vegetable gardens. Invite guest people to come and educate children and staff about gardening. | In OH&S checklists, add this area to the maintenance section. Review at staff workshops Ask parents if they want to help out in the gardens. Include updates in newsletters. Harvest and cook veges with the lunches for the children. | To be in place by end May. Review every month. | Vege gardens dug up and soil refreshed by the gardener. (Feb 2012) Rainbow Eagle presented caretakers of the land and planted seeds and seedlings with the children April 26 2012. |